## Sheet1
Ranking | Threats (1) | Vulnerabilities (2) | Contextual factors | Risks (3) | Likelihood from 1 to 5 | Impact from 1 to 5 | Reduction of Threats (Acceptance Strategy) | Reduction of Vulnerabilities (Protection Strategy) | Level of residual Risk
4 - Low | Errors and delays | Lack of experience can lead to unawareness of potential risks and challenges | A team member may not be familiar on how to complete a particular task | Lack of personal experience | 2 | 1 | Mistakes may occur due to inexperience | Other memebrs of the team will guide anyone who is in need of help with their task | 4 - Low
6 - Low | Inefficient resource allocation | Communication breakdown | Unclear understanding of requirements | Poor management process | 2 | 2 | Establish commitement to continuous management procecces | Regular performance evaluations | 6 - Low
8 - Medium | Delays | Overrliance on specific members | Features that are pre-requisites to others | Task dependencies | 3 | 2 | Create contingency plan for potential delays | Ensure open communication to stay aware of dependancies | 8 - Medium
8 - Medium | Delays | Lack of expertise | Optimistic time constraints | Inncaurate time estimates on tasks | 2 | 3 | Encourage learning from estimation mistakes | If provided, refer to past task to improuve accuracy of estimates for similar tasks | 8 - Medium
10 - Medium | Delays | Communication breakdown | External factors out of our control | Unplanned absences | 1 | 5 | Develop policies for managing unplanned absences | Update plans to adapt to changing team dynamics | 10 - Medium
Note on A1: ACF: Using the 5 levels of risk matrix (very low, low, medium, high, critical) developped in the User note, evaluate the level of risk. Level of risk = Likelihood x Impact The highest level of risk take the 1st place and so on until the lowest level of risk
Note on B1: ACF: Using the User note and the document "List of threats and related risks", mention the identified threats towards ACF according to the area context and specify if the threats are "direct", "indirect" or "crime related"
Note on C1: ACF: Using the User note, mention the identified ACF vulnerabilities according to a specific threat
Note on D1: ACF: Mention the factors that are part to the context (culture, political, economical,social etc …) and that are directly related to the threat (pattern)
Note on E1: ACF: Using the document "List of threats and related risks", mention the Risks for ACF
Note on F1: ACF: Using the scale from 1 to 5 (1=very unlikely; 2=unlikely; 3=possible; 4=likely, 5=almost certain) developped in the User note, evaluate the likelihood that the event happen in the specific area context
Note on G1: ACF: Using the scale from 1 to 5 (1=minor; 2=negligible; 3=moderate; 4=severe; 5=critical) developped in the User note, evaluate the impact on ACF if the event happen
Note on H1: ACF: If ACF chose the ACCEPTANCE STRATEGY what should be put in place in the daily/weekly/monthly security management?
Note on I1: ACF: If ACF chose the PROTECTION STRATEGY what should be put in place in the daily/weekly/monthly security management?
Note on J1: ACF: Using the 5 levels of risk matrix (very low, low, medium, high, critical) developped in the User note, evaluate the level of residual risk. Level of residual risk = Residual Likelihood x Residual Impact